## Sheet1
PROJECT IMPLEMENTATION PLAN
No | Works | Ngô Đặng Đồng Khởi | Lê Huỳnh Giảng | Start Date | End Date | Actual Working Date | Actual End Date
1 | Related system survey
1.1 | https://www.tripadvisor.com/ | x |  | 2020-09-03 | 2020-09-10 | 2020-09-03 | 2020-09-10
| https://matadornetwork.com/ | x |  | 2020-09-03 | 2020-09-10 | 2020-09-03 | 2020-09-10
| https://www.mightynetworks.com/ |  | x | 2020-09-03 | 2020-09-10 | 2020-09-03 | 2020-09-10
1.2 | Functional review and evaluation |  |  | 2020-09-10 | 2020-09-13 | 2020-09-10 | 2020-09-13
1.3 | The technologies attached : - Authenticate via SMS - Google Map | x | x | 2020-09-03 | 2020-09-06 | 2020-09-03 | 2020-09-06
2 | Design Software
2.1 | Draw Use case diagram | x | x | 2020-09-15 | 2020-09-20
| Draw ERD | x | x | 2020-09-20 | 2020-09-25
| Draw Class diagram | x |  | 2020-09-25 | 2020-09-30
| Draw Sequence diagram |  | x | 2020-09-25 | 2020-09-30
2.2 | Design screen of Website | x | x | 2020-10-01 | 2020-10-20
| Design our website's activity stream | x | x | 2020-10-01 | 2020-10-20
2.3 | Detailed database design | x | x | 2020-09-20 | 2020-10-05
3 | Back - End
3.1 | Code first for Database | x | x | 2020-10-06 | 2020-10-10
3.2 | Code API: - CRUD - Relationship | x | x | 2020-10-21 | 2020-11-10
4 | Front - End
4.1 | Login / Logout | x | x | 2020-11-01 | 2020-11-05
4.2 | Home Page | x | x | 2020-11-06 | 2020-11-15
4.3 | Admin Interface | x | x | 2020-11-06 | 2020-12-06
4.4 | User Interface | x | x | 2020-12-07 | 2021-12-20
5 | Apply other technologies
5.1 | Authenticate via SMS | x | x | 2020-12-21 | 2020-01-05
5.2 | Google Map | x | x | 2020-12-21 | 2020-01-05
5.3 | Payment Method | x | x | 2020-12-21 | 2020-01-05
6 | Hosting Website
6.1 | Hosting front-end | x | x | 2020-01-06 | 2020-01-08
6.2 | Hosting database | x | x | 2020-01-06 | 2020-01-08
7 | Testing
7.1 | Test logic error | x | x | 2020-01-09 | 2020-01-12
7.2 | Fix warning | x | x | 2020-01-09 | 2020-01-12
8 | Write a report
8.1 | Documents | x | x | 2020-01-01 | 2020-10-10
8.2 | Power Point | x | x | 2020-01-01 | 2020-10-10