## Sheet1
PROJECT IMPLEMENTATION PLAN
Type of work | Works | Ngô Đặng Đồng Khởi | Lê Huỳnh Giảng | Start Date | Deadline | State | Actual Working Date | Actual End Date | Note
Stuty | https://www.tripadvisor.com/ | x |  | 2020-09-03 | 2020-09-10 | 70% | 2020-09-03 |  |  | mm/dd/yyyy
| https://matadornetwork.com/ | x |  | 2020-09-03 | 2020-09-10 | 70% | 2020-09-03 |  |  | To do
| https://www.mightynetworks.com/ |  | x | 2020-09-03 | 2020-09-10 | 70% | 2020-09-03 |  |  | Doing
| Authenticate via SMS | x | x | 2020-10-01 | 2020-12-01 | 50% | 2020-10-01 |  |  | Pending
| Google Map | x | x | 2020-10-01 | 2020-12-01 | 50% | 2020-10-01 |  |  | Done
Design | Design UML
| Draw Use case diagram | x | x | 2020-09-15 | 2020-11-15 | 30% | 2020-09-15 |  | link
| Draw ERD | x | x |  | 2020-11-15
| Draw Class diagram | x | x |  | 2020-11-15
| Draw Sequence diagram | x | x |  | 2020-11-15
| Design screen of Website | x |  |  | 2020-11-15
| Design our website's activity stream | x | x |  | 2020-11-15
| Detailed database design | x | x |  | 2020-11-15
Back - End
| Structure of project | x | x
| Code API: - CRUD - Relationship | x | x
Front - End
|  | x | x
| Home Page | x | x
| Admin Interface | x | x
| User Interface | x | x
|  | x | x
Develop | week1 |  |  | 2020-10-05 | 2020-10-10 |  |  |  | confluence
| week2 |  |  | 2020-10-12 | 2020-10-17
| week3 |  |  | 2020-10-19 | 2020-10-24
| week4 |  |  | 2020-10-26 | 2020-10-31
| week5 |  |  | 2020-11-02 | 2020-11-07
| week6 |  |  | 2020-11-09 | 2020-11-14
| week7 |  |  | 2020-11-16 | 2020-11-21
| week8 |  |  | 2020-11-23 | 2020-11-28
| week9 |  |  | 2020-11-30 | 2020-12-05
| week10 |  |  | 2020-12-07 | 2020-12-12
Deloy | Web API + Data |  |  | 2020-10-10 | 2020-12-15
| Angular web |  |  | 2020-10-10 | 2020-12-15
Report | Word |  |  | 2020-12-14 | 2020-12-19
| Power Point |  |  | 2020-12-14 | 2020-12-19